Terms of Reference

Occupational and State Educational Standard Development Expert for Priority Occupations and Specialties

| Project | ADB Grant #0553-KGZ: Skills for Inclusive Growth Sector Development Program |
| --- | --- |
| Qualification | Occupational and State Educational Standard Development Expert for Priority Occupations and Specialties |
| Source | National | Category | Independent |
| Background With the support of the Asian Development Bank (ADB), the Ministry of Education and Science (MOES) of the Kyrgyz Republic is implementing the Skills for Inclusive Growth Sector Development Program (SIGSDP) project, which aims to improve the effectiveness of vocational education. The Program plans to provide further training to primary (PVEI) and secondary vocational educational institution (SVEI) technical educational specialists in the Occupational Standards (OSs) Development and Approval Methodology and the Industry-Specific Qualifications Framework Development Methodology as the most important components of the National Qualifications System, as the basic competency-based training concept and the most important condition for training market-demanded specialists. These Terms of Reference aim to provide technical support in the development and approval of OS and State Educational Standards (SES) for 19 SVE specialties and 10 PVE occupations. |
| Tasks Conduct a training on “The Occupational Standard Development and Approval Methodology” for the SIGSDP SVEIs and PVEIs (50 participants, 3 days, Q1 2023). Conduct a training on “The State Educational Standard Development Methodology” for PVEI and the MOES Republican Scientific and Methodological Center (RSMC) staffs (35 participants, 3 days, Q1 2023). Conduct eight trainings on “The Occupational Standard Development and Approval Methodology and the Industry-Specific Qualifications Framework Development Methodology” for the SIGSDP SVEIs and PVEIs with OS drafting for the specialties and occupations (30-40 participants in each training in Bishkek, Kara-Balta, Tokmok, Naryn, Balykchy, Osh, Jalal-Abad, Kyzyl-Kiya, Q2-4 2023). Carry out the harmonization and examination of PVE and SVE OSs prepared by PVEIs and SVEIs and employers (19 SVE OS and 10 PVE OS) with the Ministry of Labor, Social Security and Migration (MLSSM) of the Kyrgyz Republic. Accompany and advise the RSMC and Vocational Lyceums (VL) staffs in the SES development for 10 priority occupations. Duration (62 man-days in 2023) Task / Work Man-Days Period 2 trainings in Bishkek 12 days (6 (3*2) training days + 6 preparation/reporting days) Q1 2023 Trainings in Bishkek, Kara-Balta, Tokmok, Naryn, Balykchy, Osh, Jalal-Abad, Kyzyl-Kiya 37 days (18 training days + 19 preparation/reporting days) Q2 2023 OS examination and approval (incl. revision, if necessary) by the MLSSM 3 days Q3 2023 SES development consultations for 10 PVE occupations 10 days TOTAL 62 days Program Support The Program shall provide the necessary information on previous Program work and OS development, as well as contacts of responsible PVEI and SVEI persons. The Program shall cover the Expert's travel expenses to the PVEIs and SVEIs; provide the Expert with administrative and organizational support by the relevant PIU staff. Deliverables Participant lists, presentations and other training materials; MLSSM-approved OSs (19 SVE OS and 10 PVE OS), as well as official website links to those OSs. Each OS shall be accompanied by scanned minutes of the working / expert group meetings, etc.; Draft SESs for 10 RSMC-adopted priority occupations; Final descriptive work report with recommendations for further work, as well as brief descriptive reports on each training outcomes. Qualifications Higher education in the relevant field -- 10%; At least 1 year experience in the SVE and PVE OS development and examination, incl. the methodology approved by the Cabinet of Ministers of the Kyrgyz Republic (Resolution No. 77 dated July 15, 2021) -- 40%; At least 3 years of work experience in vocational education and training institutions -- 20%; At least 2 years of SES development experience -- 20%; Knowledge of Kyrgyz and Russian, as well as computer skills (Windows, MS Office, Internet Explorer) -- 10%. Reporting The Expert shall report to the SIGSDP PIU Manager and provide; Participant lists, presentations and other training materials; MLSSM-approved OS (19 SVE OS and 10 PVE OS), as well as official website links to those OSs. Each OS shall be accompanied by scanned minutes of the working / expert group meetings, etc.; Draft RSMC-adopted SESs for 10 PVEI priority occupations; Final descriptive work report with recommendations for further work, as well as brief descriptive reports on each training outcomes. Cost Estimate Remuneration for 62 days from _____________2023 through ____________2023 KGS 7500 x 62 days = KGS 465,000 |
| Place of Assignment: | Days/Settlement period | (dd /mm/ yy) |
| Bishkek office | 62 days | Beginning of Assignment March2023 |